## Planning
Planning
Elève | Zeina Alsawaf | [11 empty] | Classe | 300231
Projet | TV-Murten 1.Liga / D1 | [11 empty] | Module |  | 151
| Bloc 1 |  |  | Bloc 2 |  |  | Bloc 3 |  |  | Bloc 4 |  |  | Bloc 5
Tâches | 28.01.2025 - MAT | 28.01.2025 - A-M | 29.01.2025 - MAT | 03.02.2025 - MAT | 03.02.2025 - A-M | 04.02.2025 - MAT | 10.02.2025 - MAT | 10.02.2025 - A-M | 11.02.2025 - MAT | 17.02.2025 - MAT | 17.02.2025 - A-M | 18.02.2025 - MAT | 24.02.2025 - MAT | 24.02.2025 - A-M | 25.02.2025 - MAT
Exercices / découverte | x | x | x | x | x |  | x
Documentation
Analyse
Présentation du projet/ Cahier de charge |  |  |  |  | x
Usecase |  |  |  |  | x | x
Les maquettes |  |  | x | x
Diagramme d’activités |  |  |  |  | x
Diagramme de séquence système |  |  |  |  | x
Base de données – entité‐relation |  |  |  |  | x | x
Conception
Diagramme de classes partie cliente | [6 empty] | x
Diagramme de classes partie serveur | [5 empty] | x | x
Diagramme de séquence interactions | [7 empty] | x
Base de données – schéma relationnel |  |  | x | x | x | x |  |  |  | x | x
Conception des tests
Réalisation (Implémentation)
Implemetation Client: La View | [7 empty] | x | x | x | x | x
Implemetation: Visualisation des joueuse (Details à eux) | [10 empty] | x | x
Implemetation: visualisation des matches | [9 empty] | x | x
Implemetation: visualisation des statistics | [11 empty] | x
Implemetation: visualisation des "Angriff" and "Rece" | [12 empty] | x | x
Implemetation: modifier des stats | [13 empty] | x
Implemetation: Le login | [13 empty] | x
Descente de code | [14 empty] | x
Problèmes rencontrés | [14 empty] | x
Tests fonctionnels | [14 empty] | x
Hébergement | [14 empty] | x
Tests de l'application | [13 empty] | x | x

## Journal de travail
Journal de travail - 151
Elève / classe | Zeina Alsawaf / 300233
Projet | TVMurten-Statics
Semaine | Date | Travail effectué | Temps d'exécution [heures]
1. Semaine | 2025-01-28 | Introduction to the module / Presentation | 1.5
| 2025-01-28 | Module exercises (3 - 5) | 5.5
| 2025-01-29 | Module exercises (6 - 8) | 1.5
| 2025-01-29 | The Client's wireframes (Maquettes) | 1.5
| 2025-01-29 | Database – Entity-relationship model | 0.5
2. Semaine | 2025-02-03 | Presentation, video, and additional information for the module | 1
| 2025-02-03 | Exercises 9 & 10 | 1.5
| 2025-02-03 | Database – Data insertion | 1.5
| 2025-02-03 | Client's wireframes (Maquettes) – Modifications | 1
| 2025-02-03 | Use Case | 1
| 2025-02-03 | Activity diagram -> display Statistics per Match and per Player | 0.5
| 2025-02-03 | System sequence diagram -> display Statistics per Match and per Player | 0.25
| 2025-02-03 | Project presentation / Project Specifications | 0.25
| 2025-02-04 | Database – Relational schema -> modifications | 1
| 2025-02-04 | Presentation, video, and additional module information | 0.5
| 2025-02-04 | Redoing the Use Case (accidentally deleted) | 0.5
| 2025-02-04 | Class diagram: Server | 1.5
3.Semaine | 2025-02-10 | Video & Exercise 11 | 0.75
| 2025-02-10 | Class diagram: Server | 2
| 2025-02-10 | Class diagram: Client | 0.75
| 2025-02-10 | Interaction sequence diagram | 1
| 2025-02-10 | Client implementation: View | 2.5
| 2025-02-11 | iSQL, HTML & JS injection – Group presentation | 1.5
| 2025-02-11 | Client implementation: View | 2
| 2025-02-16 | Documentation: Analysis & Conception part | 3
4.Semaine | 2025-02-17 | Morning introduction & video | 0.5
| 2025-02-17 | Filling the database with static data | 1.5
| 2025-02-17 | Implementation: Match visualization | 2
| 2025-02-17 | Implementation: Player visualization (detailed view) | 1.5
| 2025-02-17 | Client implementation: View | 1
| 2025-02-17 | Group testing exercises & presentation | 0.5
| 2025-02-18 | Implementation: Player visualization (detailed view) | 1.5
| 2025-02-18 | Client implementation: View | 1
| 2025-02-18 | Implementation: Statistics visualization | 1
5.Semaine | 2025-02-19 | Client implementation: View | 4
| 2025-02-19 | Implementation: Statistics visualization | 4
| 2025-02-21 | Implementation: the Login -> Sessions | 6
| 2025-02-21 | Implementation: Complete structural changes | 3
| 2025-02-22 | Implementation: Visualization of "Angriff" and "Rece" | 4
| 2025-02-22 | Client implementation: View | 2
| 2025-02-24 | Implementation: Modify statistics | 2
| 2025-02-24 | Issue: Parameters were empty when modifying statistics | 3
| 2025-02-24 | Solution: Parameters were incorrectly passed in indexCtrl.js | 2
| 2025-02-24 | Implementation: Modify statistics | 3
| 2025-02-24 | Implementation: Hashing an already existing password | 1
| 2025-02-24 | Issue: Cannot perform a PUT action with both updateAngriffs and updateReces simultaneously | 0.5
| 2025-02-24 | Solution: Check the parameters before executing the update | 0.5
| 25/02/205 | Finalizing the website (view, code, minor bug fixes) | 2
| 25/02/205 | Code comments | 1
| 25/02/205 | Documentation | 6
| 25/02/205 | Resolving issues with updateAngriff / updateRece | 2
| 26/02/205 | Code review | 0.5
| 26/02/205 | Problems encountered | 0.5
| 26/02/205 | Functional testing | 1
| 26/02/205 | Deployment & hosting (Hébergement) | 1
| 26/02/205 | Project finalization | 2
| 26/02/205 | correcting syntax errors | 1
| Total |  | 97
A mettre :
· Toutes les tâches effectuées sur le projet
o Les problèmes rencontrés
· Toutes les rencontres avec le professeur
o Ce qui a été contrôlé
o Ce qui a été décidé

## tests
Protocole de test
Utilisateur | Cas | Tests | Attendu | Google Chrome | Edge | Firefox
Visitor | review the rece and angriff statistics for the selected player and selected match. | the visitor chooses a player by clicking on their "View stats" button and then chooses a Match from the combobox to review their chosen player rece and angriff stats | review NOK. Unlogged users can't access to the html view that manages the function without logging in first.
User | review the rece and angriff statistics for the selected player and selected match. | The logged in user chooses a player by clicking on their "View stats" button and then chooses a Match from the combobox to review their chosen player rece and angriff stats | review OK, the Rece and Angriff stats should display as well as the "modify" Button but the logged user cant modify anything.
| the logged in User tries to modify the rece table field "Punkte". | the User tries to enter the value= "10', matchPk = 1; DROP TABLE angriff_table; -- " when modifying the "document.getElementById("angriffPunkte").textContent" Element | modification NOK, a User cannot modify
U
Admin | review the rece and angriff statistics for the selected player and selected match. | The Admin chooses a player by clicking on their "View stats" button and then chooses a Match from the combobox to review their chosen player rece and angriff stats | review OK, the Rece and Angriff stats should display as well as the "modify" Button.
| modify the stats of the chosen player and the chosen match | the admin chooses a player by clicking on their "view stats" Button and then chooses a Match from the combobox. The Admin then modifies the numbers in the rece and angriff table and then clicks on "speichern". | modification OK, the Admin has the right to modify the data.
| modify the stats of the chosen player and the chosen match | the admin chooses a player by clicking on their "view stats" Button and then chooses a Match from the combobox. The Admin then modifies the numbers in the rece and angriff table and add the number "111111111111111111111111" in the rece field "perfekt" then clicks on "speichern". | modification NOK, the number passed the maximal VARCHAR limits.
| the admin tries to modify the rece table field "Punkte". | the admin tries to enter the value= "10', matchPk = 1; DROP TABLE angriff_table; -- " when modifying the "document.getElementById("angriffPunkte").textContent" Element | SQL injection prevented.

## tests-conclusion
Protocole de test
Utilisateur | Cas | Tests | Attendu | Obtenu | Resultat | Scrennshot
Visitor | review the rece and angriff statistics for the selected player and selected match. | the visitor chooses a player by clicking on their "View stats" button and then chooses a Match from the combobox to review their chosen player rece and angriff stats | review NOK. Unlogged users can't access to the html view that manages the function without logging in first. | review NOK: Visitor can go through the navigator but can't review any data. | OK, Zeina Alsawaf the 25.02.2025 | #VALUE!
User | review the rece and angriff statistics for the selected player and selected match. | The logged in user (CucheT) chooses a player by clicking on their "View stats" button and then chooses a Match from the combobox to review their chosen player rece and angriff stats | review OK, the Rece and Angriff stats should display as well as the "modify" Button but the logged user cant modify anything. | the User CucheT navigates to the "SpielerStatistik" tap and selects a player. they then select a Match and the rece&Angriff statistics displayed according to the chosen data | OK, Zeina Alsawaf the 25.02.2025 | #VALUE!
| the logged in User tries to modify the rece table field "Punkte". | the User tries to enter the value= "10', matchPk = 1; DROP TABLE angriff_table; -- " when modifying the "document.getElementById("angriffPunkte").textContent" Element | modification NOK, A Message that say ""Update failed: Administrator access required" should display to the client | A Message that says "Update failed: Administrator access required" displayed, and no modification were made in the database | OK, Zeina Alsawaf the 25.02.2025 | #VALUE!
U
Admin | review the rece and angriff statistics for the selected player and selected match. | The Admin (MeierP) chooses a player by clicking on their "View stats" button and then chooses a Match from the combobox to review their chosen player rece and angriff stats | review OK, the Rece and Angriff stats should display as well as the "modify" Button but the logged user cant modify anything. | the Admin MeierP navigates to the "SpielerStatistik" tap and selects a player. they then select a Match and the rece&Angriff statistics displayed according to the chosen data | OK, Zeina Alsawaf the 25.02.2025 | #VALUE!
| modify the stats of the chosen player and the chosen match | the admin chooses a player by clicking on their "view stats" Button and then chooses a Match from the combobox. The Admin then modifies the numbers in the rece and angriff table and then clicks on "speichern". | modification OK, the Admin has the right to modify the data. | modification OK, a Message that says "" | OK, Zeina Alsawaf the 25.02.2025 | #VALUE!
| modify the stats of the chosen player and the chosen match | the admin chooses a player by clicking on their "view stats" Button and then chooses a Match from the combobox. The Admin then modifies the numbers in the rece and angriff table and add the number "111111111111111111111111" in the rece field "perfekt" then clicks on "speichern". | modification NOK, the number passed the maximal VARCHAR limits. | modification NOK, an error messaged displayed. | OK, Zeina Alsawaf the 25.02.2025 | #VALUE!
| the admin tries to modify the rece table field "Punkte". | the admin tries to enter the value "105 ; DROP TABLE alsawafz_DB_finalTVMurten.t_Angriff; --" when modifying the "document.getElementById("angriffPunkte").textContent" Element | SQL injection prevented. | SQL injection prevented. | OK, Zeina Alsawaf the 25.02.2025 | #VALUE!